## Sheet1
Shopkeeper Inventory and POS App
Task Name | Start Date | End Date | Duration | Roles | Progress | FeedBack
Project Planning: | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 days | Muhammad Awais | Done
Bussines Analysis: | 2023-12-30 | 2024-01-02 | 4 days | MUHAMMAD AREEB | In progress
Requirements Gathering and Analysis: | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 days | Muhammad Awais | Done
UI/UX Design:
Documentation:
SRS | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 days | Muhammad Awais | Done
UI/UX | 2023-12-29 16:00 | 2024-01-06 08:30 | 4 days | Hasnain shabir | Done
Sign Up And Login | 2024-01-06 10:00 | 2024-01-12 13:00 | 6 days | Hasnain Sher | Done
Home Page and Dashboard | 2024-01-06 10:00 | 2024-01-12 13:00 | 6 days |  | To Do
Create and Join Committee | 2024-01-06 10:00 | 2024-01-14 13:00 | 8 days | Muhammad Awais | Done
Backend Development: | 2024-01-13 10:00 | 2024-01-21 17:00 | 8 days | Adil | In progress
Database Design: | 2023-01-13 10:00 | 2024-01-21 17:00 | 8 days | Adil | To Do
Barcode Scanning Integration: | 2024-01-21 10:00 | 2024-01-21 17:00 | 8 days |  | To Do
Inventory Management /Add Product | 2024-01-21 18:30 | 2024-01-25 15:30 | 4 days | Hasnain Sher | Done
Point-of-Sale System: | 2024-01-25 16:00 | 2024-01-25 20:00 | 1 days |  | To Do
User Authentication and Security: | 2024-01-25 16:00 | 2024-01-25 20:00 | 2 days |  | To Do
Testing: | 2024-01-25 16:00 | 2024-01-25 20:00 | 3 days | Updesh Muni | To Do
Deployment: | 2024-01-25 16:00 | 2024-01-25 20:00 | 4 days |  | To Do
Final Documentation: | 2024-01-25 16:00 | 2024-01-25 20:00 | 5 days | Muhammad Awais | In progress
Marketing and Launch: | 2024-01-25 16:00 | 2024-01-25 20:00 | 6 days | Muhammad Awais | To Do